## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E01a | add new customer | As a Bank Employee, I want to obtain a customer’s information like name, address, date of birth and get the type of account they want to open, so that once the information is verified, I can enter them to the system. | 1 | 1 | 1.make sure the customer provide the sufficient information to open an account. 2.get the account type the customer want to open. | record inoformation | 4,19 | 4,20
E01b | confirm credit status | As a Bank Employee, I want to send customer information to the credit agency and get a feedback, so that I can carry on opening an account. | 1 | 1 | 1.verify the facticity of the customer’s information. | verify information | 4,19 | 4,20
E01c | create accounts | As a Bank Employee, I want to create an account of the type chosen from the customer, generate a unique account number and pin, so that I can create a account with the confirmed information of the customer | 1 | 1 | 1.verify the type of account is credited. 2.verify the account number is unique | verify credit and check account number | 4,19 | 4,20
E02a | deposit funds | As a Depositor, I want to supply the account number and the amount of funds to be deposited, so that I can deposit funds to the account. | 1 | 1 | 1.verify the existence of account number 2.verify the status of the account number 3.show the amount of money you have successfully deposited | verify account number and the amount of funds successfully deposited | 4,19 | 4,20
E03a | check funds to be cleared | As a Clearing System, I want to receive the account number of the customer, so that I can clear the funds for the specific customer’s card | 5 | 3 | 1.receive correctly account number 2.give a feedback to customer | show how much funds have been cleared | 4,21 | 4,22
E03b | check funds request | As a Customer, I want to provide a account to the clearing system, so that clearing procedure can continue | 5 | 3 | 1.provide correct account number | account number | 4,21 | 4,22
E04a | customer information check | As a Bank System, I want to obtain the information which customer enters, so that I can verify the account number and pin for further withdrawal action | 1 | 2 | 1.obtain customer’s information and verify them | account number and related pin | 4,20 | 4,21
E04b | judge account status | As a Bank System, I want to obtain the account number and pin, so that I can judge the account type of customer and whether the account is suspended for providing a correspond withdrawal services for the customer | 1 | 2 | 1.search the bank system to get the correct account type 2.provide a feedback of the account type | account number and account type | 4,20 | 4,21
E04c | withdraw funds request | As a customer of saver account, I want to enter account number and pin to send a request for withdrawal funds, so that I can withdraw funds in the following days | 1 | 2 | 1.check account number and pin 2.check account type 3.send request | account type and request | 4,20 | 4,21
E04d | check account balance | As a Bank System, I want to obtain the account number, so that I can check the balance of the account for further procedure of withdrawal | 1 | 2 | 1.verify the balance of account according to the account number | account number, balance | 4,20 | 4,21
E04e | withdraw funds | As a customer, I want to enter my account number, pin and the amount of funds I want to withdraw, so that I can withdraw funds if I have enough funds. | 1 | 2 | 1.check account number and pin 2.check remaining funds in cards and compare it with the amount customer want to withdraw to determine whether the trade can be successful | account number and related pin, amount of funds customer want to withdraw | 4,20 | 4,21
E05a | suspend account | As a customer, I want to enter account number and pin to freeze my account in some situation by noticing bank system, so that I can suspend account for protecting my account and funds | 5 | 3 | 1.verify the account number and correspond pin the customer input 2.freeze the account if verified | account number and related pin, freeze account | 4,21 | 4,22
E05b | re-instate account | As a customer, I want to enter account number and pin to re-active the suspended account, so that I can re-instate the suspended account for normal operation | 5 | 3 | 1.verify the account number and correspond pin the customer input 2.re-instate the account if verified | account number and related pin, re-instate account | 4,21 | 4,22
E06a | check account balance | As a Bank System, I want to obtain the account number, so that I can check the balance of the account for further procedure of closing account | 2 | 3 | 1.verify the balance of account according to the account number | account number, balance | 4,21 | 4,22
E06b | close account | As a customer, I want to enter account number and pin to be closed, so that I can close my account if the balance of it is zero. | 3 | 3 | 1.verify the account number and correspond pin the customer input 2.balance of the account is zero | account number and related pin, balance is zero | 4,21 | 4,22